GIVING HOPE

The Giving Hope Christmas Experience:  Basic Components

- This is an Outreach to families* in the community that are in need.  Great opportunity to share Jesus and invite an entire family to our church.

- Selected Families are by invite only and have scheduled appointment times.

- Selected Families will hear a Christmas Video Message from Pastor Dino and also have the opportunity to pray with our ministry team.

- Parents will get to work with a shopping buddy to personally shop for their children and have the gifts wrapped by our team.

- The children will get their own special experience to enjoy music, food and hear the Christmas story while parents shop.

- Giving Hope Christmas Experience Serving opportunities sign up on line or at the Giving Hope table.    https://www.churchofthehighlands.com/hope

*Families who are members of our church should be extended help through our benevolence process and pastoral care team.

Timeline

- Gather receiving children/families names & info

- November 6th  thru November 27th Giving Hope Info Booths at every campus

- November 6th & 13th Packets Available for adoption at every campus (while packets last)

- November 27th  Gifts due back to campus

- December 1st  Send out invites to families

- December 17th Giving Hope Christmas Experience for recipients (hosted at locations above)

See additional info on back

Important Information

- Determine ministry partner(s) for surplus gifts to be given after event

- Locate Giving Hope Banner.  Notify Central if you do not have one.

- Invitations for receiving families will be created, printed and sent to campuses from Central.  Let Central know how many you need.

- Plan December First Saturday Serve for event prep

- Reserve Temporary storage for donated gifts (pod)

- Dream Team Serve Food – Central will be giving campuses food options for the event thru Sysco in upcoming weeks.

- SERVE signup is online only at https://www.churchofthehighlands.com/hope   Site will be updated and made public by Nov. 6th

- Background Checks & Kids Check-in.  Ensure that you have this team trained and ready.

- Determine number of children/families your campus can accommodate based on your venue and dream team size.  After determining the number of children/families you can serve then determine number of packets to create.  (2-3 times as many packets as children)  Don’t limit people’s generosity.  Let them give as many gifts for that packet as they desire.

Use these ratios as a guide for creating packets

| Age | BOY | GIRL |
| --- | --- | --- |
| 0-3 | 4% | 4% |
| 4-6 | 12.5% | 12.5% |
| 7-9 | 12.5% | 12.5% |
| 10-12 | 12.5% | 12.5% |
| 13 & up | 8% | 8% |